## Event Process Checklist
Comp? | Primary | Support | Description | When (Deadline) | Comments, Background
Establishing responsibiltiies
| RD | CC | Chapter established and organized to carry out event |  | Chartered, Class B license?
| ED | RD | Primary RD: Back-up RD: | January | Each year
| CC |  | Chapter Chair: Treasurer: |  | Bank signature card?
| RD |  | CC provided copy of this checklist, and web address for chapter support material
Schedule the event and solicit sponsors
| CC | RD | Select date for event: |  | Ensure deconflicted with other WWA events
| CC |  | Select event venue and identify charges |  | Dinner (about $15-20), WWA Membership ($25), small door prize with WWA logo (<$5); Not trying to make money off the entry cost.
| CC |  | Solicit major sponsors and donors |  | Early tp get "presenting sponsor" on initial flyers
| RD |  | Report status of Scheduling to ED
Pre-event Planning: Class "A"
| CC | RD | Plan Class "A" Pre-event raffle? | 5 Mo before | Need not be present, use "General/Special Raffle Worksheet": ticket template; wisducks.org/chapter-information page
| RD | CC | Proof Class A ticket
| RD |  | Print class A tickets and forward to chapter |  | who, where (Jim Tooni option)
| CC | RD | Mail stock (20-30 tickets) to Kelcy for online sales
| CC | RD | Market Class "A" raffle: ___WWA website; ___ Facebook; ____Local distribution; ______Poster
|  |  | Report status of Pre-event planning to ED | 5 mo prior | Class event ?; Organizational update
Phase 1 (Early) Plan the event
| CC | RD | Establish attendee "goal": |  | Be conservative in estimates, but about $100/attendee will be spent after dinner ticket
| CC | RD | Complete Pre-event Budgeting | 5 mo before | "Pre-Banquet Budgeting form" -
| CC | RD | Gun philosophy and numbers… what guns to have? Determine "hot" guns |  | Quality vs quantity, remember that there are 7:1 deer hunters vs waterfowlers in WI
| CC |  | Decide on gun dealer; Put gun cost estimates into budget, get bids | 4 Mo before | put estimated gun costs into budget
| CC | RD | Identify basic outline of Games / Raffles / Prizes, put non-gun costs into budget |  | Gun Boards, Tactacam, Games, Walkarounds, Bucket raffles. Games may have an appeal to attendees who have already placed their raffle $$--a game offers entertainment.
| CC | RD | Finalize printed/flyer gun list | 3-4 Mo. Before
| CC | RD | Decide table and ticket options
| RD | CC | Chair and RD review plan. Finalize Pre-Event Budget Form | 4 Mo before | Report planned attendance
| RD |  | Report Status of Phase 1 Planning ot ED | 3 mo before | "Shape" of event and help required; Budget outlook
Market the event
| RD | CC | Discuss flyer - discuss updates to prior year | 4 Mo before | RD has template
| RD | CC | Drafting/finalizing flyer | 10 wks before
| CC | RD | Review and update mailing list with Kelcy - changes made?
| RD | CC | Order Flyers from printer - who sends out? | 10 wks before (min) | Who will send out - printer, chapter?
| CC | RD | Order dinner tickets from Printer | 4 wks before | Order with flyer
| CC | AD | Post e-flyer on website | 10 wks before (min)
| CC | AD | Evite and facebook | 4-6 wks before | Communicate future marketing wishes with Kelcy
| ED |  | Boost FB post? | 4 wks before | Costs maybe $5-10 per day
| CC |  | Marketing: Post flyers around town | 8 wks before
| CC |  | Call previous attendees to ensure they are aware and coming | 3-4 wks before | If appropriate
| RD |  | Report status of Marketing to ED | 5 weeks prior | "Shape" of event and issues
Phase 2: Plan the Event
| CC | RD | Consider state sponsor offerings and state inventory | 4 Mo before
| CC | RD | Pre-Order inventory from state | 4 Mo before
| RD |  | Ensure adequate ticket inventory | 1 Mo before
| CC |  | Determine menu | 3-4 Mo before
| CC | RD | Receive dinner tickets | 3.5 Mo before | Confirm shipped/received
| RD |  | Finalizing event gun board tickets, ship/deliver to chapter | 6 wks before
| CC |  | Meet with venue (meal count, table setup, volunteer meals/timing) | 3-4 wks prior
| CC |  | Finalize sponsors (gun board presenters, or presenting sponsor or…) Design game/raffle signage - share with RD | 3-4 wks prior
| CC |  | Receive tickets | 3 weeks prior
| CC | RD | Evaluate # of donations--enough? (Bucket raffle, door prizes,…) last ditch effort by Committee | 2 wks before
| CC | RD | Finalize state inventory needs | 2 wks before
| CC |  | Solicit volunteers to help run the event.
| CC |  | Arrange volunteer meals to not interfere with event
| CC |  | Provide final attendance numbers to catereer | 10 days
| CC | RD | Update budget for attendance |  | Adjust games and prizes for actual attendees. Now consider estimated costs (Guns, dinner, hall rental, prizes, other costs).
| RD |  | Report status of Planning to ED |  | Number of attendees; Estimated Net vs Budget; Issues; help required
Prepare for the event
| RD | AD | Send chapter online order summary | 1 week pre-event
| CC |  | Assemble advance ticket packages | 1 week pre-event | Not later than…
| CC | RD | Create registration sheet | 6 weeks pre-event | To collect names and packages
| CC | RD | Identify Master of Ceremonies, develop event schedule | 2 months pre-event
| RD | CC | Make any necessary signage | 2-3 days pre-event
| RD |  | Load trailer with chapter merchandise/games/raffle equipment /signage/treasurer's case/credit card machine/inventory sheet and other supplies | 1-2 days pre-event
| RD |  | State raffle tickets (State hunt, UTV) | 1-2 days pre-event
| RD |  | Does chapter need state raffle item brought to event? | 2 weeks pre-event
| RD |  | Deliver state merchandise and equipment and set-up gear | 0-1 days pre-event
| CC | RD | Review delivered inventory against request. Transfer inventory | 0-1 days pre-event
| CC |  | Set up room: Tables, gun boards, signage, raffles, games, etc | 0-1 days pre-event | Consider traffic flow - No Dead spots
| RD |  | Prepare Silent Auction items and Sheets | 0-1 days pre-event
| RD |  | Set up games/silent auction, with buckets/tickets, fill out" Raffle ticket inventory sheet" | 0-1 days pre-event
| RD |  | Report status of preps to ED | 0-1 days pre-event
| RD |  | Bring required paperwork and credit card equipment | 0-1 days pre-event
| RD |  | Report readiness for event to ED | 2 days prior
Cash / credit needs for the event
| CC |  | Get cash (approx: $1500-3000) | 1 day pre-event | Ask RD for denominations based on games
| CC | RD | Set-up raffle pouches/aprons | 0-1 days pre-event
| CC |  | Set up cash box | 0-1 days pre-event
| RD | CC | Test credit card machine | 0-1 days pre-event
| CC | RD | Set up treasurer's station and welcome station | 0-1 days pre-event | Money/Credit Card machine
Conduct Event
| CC |  | Feed volunteers, brief them, then position them |  | Feed well priori to door opening; bried them on ENTITE event as well as their station.
| RD |  | Class A drawing - take pictures of tix and winners and provide to D of Admin
Manage walk-arounds, drawings, silent auctions
| RD |  | Arrange Photgrapher for after-event FB postings - send to ED
| RD | CC | Run through event schedule
| RD | ED | Executive Director talk
| CC |  | Closeout silent auction (taxes collected)
| CC |  | Congratulate and thank team
| CC |  | Clean-up; assist gear back into RD van
Account for the Event
| RD | CC | Double count Money by raffle / game; enter into Banquet Event Income worksheet - take picture and send to RD | Night of | RD, Treasurer, 1 other count $
| RD | CC | Turn in Inventory charge( to DA) | Night of
| RD |  | Turn in raffle ticket inventory sheet to DA | Day after
| RD |  | Turn in Membership stubs to DA | Day after
| RD |  | Turn in List of event sponsors & copy of flyer to DA | Day after
| RD |  | Sales tax report - take silent & vocal auction receipts with to fill this out | Day after
| CC | RD | Wrap-up meeting/Party | 2 weeks post-event
| CC | RD | Submit Banquet Event Income Form to DA | 30 days post-event
| CC |  | Send invoice & final check to D of Admin | 30 days post-event | $500 remains in account for next year
| AD |  | Event reconciled - report sent to chapter | 30 days post-event
| CC |  | Thanks yous to Sponsors | As soon as possible | While,fresh in minds of sponsors--pictures would be nice
| CC | RD | Committee get together to review lessons, results

## General Special Raffle WS
GENERAL/SPECIAL RAFFLE WORKSHEET
Chapter: _________________________________________________________________________________
Name of Raffle: ___________________________________________________________________________
Price of Tickets:__________________________ Ticket Color: ____________________________
|  | Prizes |  |  | Cost | Fair Market Value
1._________________________________________________________ |  |  |  |  | ________ | ________
2._________________________________________________________ |  |  |  |  | ________ | ________
3._________________________________________________________ |  |  |  |  | ________ | ________
4._________________________________________________________ |  |  |  |  | ________ | ________
5._________________________________________________________ |  |  |  |  | ________ | ________
6._________________________________________________________ |  |  |  |  | ________ | ________
7._________________________________________________________ |  |  |  |  | ________ | ________
8._________________________________________________________ |  |  |  |  | ________ | ________
9._________________________________________________________ |  |  |  |  | ________ | ________
10.________________________________________________________ |  |  |  |  | ________ | ________
|  |  |  | Total: | ________ | ________
|  |  |  | Income: | _________________
|  |  |  | Expenses: | _________________
|  |  | Net Total Income: |  | _________________
Make copies of this form for each raffle you hold

## Raffle Ticket inventory sheet
Raffle Ticket Inventory 2-Part
Total Tickets | Ticket Color | # Full Rolls | # Part Rolls | Notes
White
Yellow
Salmon
Orange
Red
Blue
Green
Purple
Teal
Gold
Olive
Grey
Pink
Rose
Blank White
Blank Yellow
Blank Salmon
Blank Orange
Blank Red
Blank Blue
Blank Green
Blank Purple
Blank Teal
Blank Gold
Blank Olive
Blank Pink
Blank Rose
Big Red
Big Blue
Big Orange
Big Purple
Big Yellow
Big Salmon
WWA Lime
WWA Lemon
WWA Orange
WWA Strawberry
WWA Raspberry
Single Style Tickets
White
Yellow
Salmon
Orange
Red
Blue
Green
Purple
Gold
Olive
Pink
Brown
Mint